## Tasks_and_priority
PRIORITY | TASK | SPRINT | Estimate(Hours) | STATUS
1 | Set up Development IDE | 26/01-09/01 | 0:30 | DONE
2 | Set up GitHub | 26/01-09/01 | 0:30 | DONE
3 | Set up Travis-CI | 26/01-09/01 | 0:30 | DONE
4 | Make sure project builds to self-contained Jar within Docker | 26/01-09/01 | 0:30 | DONE
5 | Set-up database within Docker including data-population. | 26/01-09/01 | 0:30 | DONE
6 | Design system |  |  | In PROGRESS
7 | Build the system |  |  | TO BE STARTED
8 | Generate report about all the countries in the world organised by largest population to smallest. |  | 0:10 | TO BE STARTED
8 | Generate report about all the countries in a continent organised by largest population to smallest. |  | 0:10 | TO BE STARTED
8 | Generate report about all the countries in a region organised by largest population to smallest. |  | 0:10 | TO BE STARTED
8 | Generate report about the top N populated countries in the world where N is provided by the user. |  | 0:10 | TO BE STARTED
8 | Generate report about the top N populated countries in a continent where N is provided by the user. |  | 0:10 | TO BE STARTED
8 | Generate report about the top N populated countries in a region where N is provided by the user. |  | 0:10 | TO BE STARTED
8 | Generate report about all the cities in the world organised by largest population to smallest. |  | 0:10 | TO BE STARTED
8 | Generate report about all the cities in a continent organised by largest population to smallest. |  | 0:10 | TO BE STARTED
8 | Generate report about all the cities in a region organised by largest population to smallest. |  | 0:10 | TO BE STARTED
8 | Generate report about all the cities in a country organised by largest population to smallest. |  | 0:10 | TO BE STARTED
8 | Generate report about all the cities in a district organised by largest population to smallest. |  | 0:10 | TO BE STARTED
8 | Generate report about the top N populated cities in the world where N is provided by the user. |  | 0:10 | TO BE STARTED
8 | Generate report about the top N populated cities in a continent where N is provided by the user. |  | 0:10 | TO BE STARTED
8 | Generate report about the top N populated cities in a region where N is provided by the user. |  | 0:10 | TO BE STARTED
8 | Generate report about the top N populated cities in a country where N is provided by the user. |  | 0:10 | TO BE STARTED
8 | Generate report about the top N populated cities in a district where N is provided by the user. |  | 0:10 | TO BE STARTED
8 | Generate report about all the capital cities in the world organised by largest population to smallest. |  | 0:10 | TO BE STARTED
8 | Generate report about all the capital cities in a continent organised by largest population to smallest. |  | 0:10 | TO BE STARTED
8 | Generate report about all the capital cities in a region organised by largest to smallest. |  | 0:10 | TO BE STARTED
8 | Generate report about the top N populated capital cities in the world where N is provided by the user. |  | 0:10 | TO BE STARTED
8 | Generate report about the top N populated capital cities in a continent where N is provided by the user. |  | 0:10 | TO BE STARTED
8 | Generate report about he top N populated capital cities in a region where N is provided by the user. |  | 0:10 | TO BE STARTED
8 | Generate report about the population of people, people living in cities, and people not living in cities in each continent. |  | 0:10 | TO BE STARTED
8 | Generate report about the population of people, people living in cities, and people not living in cities in each region. |  | 24:10 | TO BE STARTED
8 | Generate report about the population of people, people living in cities, and people not living in cities in each country. |  | 0:10 | TO BE STARTED
8 | make information about the population of the world, population of any continent, population of any region, population of any country, population of any district and population of any city accessible to the organisation |  | 0:10 | TO BE STARTED
8 | Provide number of people who speak chinese. |  | 0:10 | TO BE STARTED
8 | Provide number of people who speak english. |  | 0:10 | TO BE STARTED
8 | Provide number of people who speak hindi. |  | 0:10 | TO BE STARTED
8 | Provide number of people who speak spanish. |  | 0:10 | TO BE STARTED
8 | Provide number of people who speak arabic. |  | 0:10 | TO BE STARTED
9 | make sure all country reports include the columns code, name, continent, region, population and capital. |  | 0:10 | TO BE STARTED
9 | make sure all city reports include the columns name, country, district and population |  | 0:10 | TO BE STARTED
9 | make sure all capital city reports include the columns name, country and population |  | 0:10 | TO BE STARTED
9 | make sure all population reports include the name of name of the continent/region/country, the total population of the continent/region/country, the total population of the continent/region/country living in cities (including a %) and the total population of the continent/region/country not living in cities (including a %) |  | 0:10 | TO BE STARTED
1 | Final release of system |  |  | TO BE STARTED

## Kanban_Board
Backlog | Not Started | Sprint | In progress | Done | Duration
Set up Development IDE |  |  |  | X
Set up GitHub |  |  |  | X
Set up Travis-CI |  |  |  | X
Make sure project builds to self-contained Jar within Docker |  |  |  | X
Set-up database within Docker including data-population. |  |  |  | X
Design system | X
Build the system | X
Generate report about all the countries in the world organised by largest population to smallest. | X
Generate report about all the countries in a continent organised by largest population to smallest. | X
Generate report about all the countries in a region organised by largest population to smallest. | X
Generate report about the top N populated countries in the world where N is provided by the user. | X
Generate report about the top N populated countries in a continent where N is provided by the user. | X
Generate report about the top N populated countries in a region where N is provided by the user. | X
Generate report about all the cities in the world organised by largest population to smallest. | X
Generate report about all the cities in a continent organised by largest population to smallest. | X
Generate report about all the cities in a region organised by largest population to smallest. | X
Generate report about all the cities in a country organised by largest population to smallest. | X
Generate report about all the cities in a district organised by largest population to smallest. | X
Generate report about the top N populated cities in the world where N is provided by the user. | X
Generate report about the top N populated cities in a continent where N is provided by the user. | X
Generate report about the top N populated cities in a region where N is provided by the user. | X
Generate report about the top N populated cities in a country where N is provided by the user. | X
Generate report about the top N populated cities in a district where N is provided by the user. | X
Generate report about all the capital cities in the world organised by largest population to smallest. | X
Generate report about all the capital cities in a continent organised by largest population to smallest. | X
Generate report about all the capital cities in a region organised by largest to smallest. | X
Generate report about the top N populated capital cities in the world where N is provided by the user. | X
Generate report about the top N populated capital cities in a continent where N is provided by the user. | X
Generate report about he top N populated capital cities in a region where N is provided by the user. | X
Generate report about the population of people, people living in cities, and people not living in cities in each continent. | X
Generate report about the population of people, people living in cities, and people not living in cities in each region. | X
Generate report about the population of people, people living in cities, and people not living in cities in each country. | X
make information about the population of the world, population of any continent, population of any region, population of any country, population of any district and population of any city accessible to the organisation | X
Provide number of people who speak chinese. | X
Provide number of people who speak english. | X
Provide number of people who speak hindi. | X
Provide number of people who speak spanish. | X
Provide number of people who speak arabic. | X
make sure all country reports include the columns code, name, continent, region, population and capital. | X
make sure all city reports include the columns name, country, district and population | X
make sure all capital city reports include the columns name, country and population | X
make sure all population reports include the name of name of the continent/region/country, the total population of the continent/region/country, the total population of the continent/region/country living in cities (including a %) and the total population of the continent/region/country not living in cities (including a %) | X
Implement system | X
Deploy system | X